|  |
| --- |
| **Amendment -1**  **Tender No. HLL/ID/13/46 dated 05.06.2013** |
| **Sub:** Amendment for the work : Construction of Gallery Building For Proposed Regional Science Centre, Chalakkudy  The time of completion of the work is amended as **12 months** instead of 15 months as in tender document. |

Deputy Vice President (Tech)

HLL Lifecare Limited

Infrastructure Development Division